## DP1.0
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: | Mike Nguyen |  |  | Activity Log for First Design Project 1.0 (organisation & template reports)
Full Student Number: | 301545780
Group Number: | G30
Members Relative Contribution: (estimate your contribution to this phase of the project) | 40%
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
| 5780 | 2026-01-30 | 14:05 | 14:35 |  | Read Design Project 1 specification document; identified required deliverables for DP1.0 and mapped report outline sections to specification headings. | 0.5
| 5780 | 2026-01-30 | 16:00 | 17:00 |  | Created DP1 root directory and subfolder hierarchy according to Project Documentation Guidelines; verified compliance with DP1.0 submission rules. | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
1.5

## DP1.1
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: |  |  |  | Activity Log for First Design Project 1.1 (project research, development & documentation)
Full Student Number:
Group Number: | Gxx
Members Relative Contribution: (estimate your contribution to this phase of the project) | %
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## DP1.2
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: |  |  |  | Activity Log for First Design Project 1.2 (project revision)
Full Student Number:
Group Number: | Gxx
Members Relative Contribution: (estimate your contribution to this phase of the project) | %
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## DP2.0
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: |  |  |  | Activity Log for Second Design Project 2.0 (organisation & template reports)
Full Student Number:
Group Number: | Gxx
Members Relative Contribution: (estimate your contribution to this phase of the project) | %
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## DP2.1
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: |  |  |  | Activity Log for Second Design Project 2.1 (project research, development & documentation)
Full Student Number:
Group Number: | Gxx
Members Relative Contribution: (estimate your contribution to this phase of the project) | %
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## FP
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: |  |  |  | Activity Log for Final Project (project research, development & documentation)
Full Student Number:
Group Number: | Gxx
Members Relative Contribution: (estimate your contribution to this phase of the project) | %
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0