## DP1.0
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: | Mike Nguyen |  |  | Activity Log for First Design Project 1.0 (organisation & template reports)
Full Student Number: | 301545780
Group Number: | G30
Members Relative Contribution: (estimate your contribution to this phase of the project) | 40%
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
| 5780 | 2026-01-30 | 14:05 | 14:35 |  | Read Design Project 1 specification document; identified required deliverables for DP1.0 and mapped report outline sections to specification headings. | 0.5
| 5780 | 2026-01-30 | 16:00 | 17:00 |  | Created DP1 root directory and subfolder hierarchy according to Project Documentation Guidelines; verified compliance with DP1.0 submission rules. | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
1.5

## DP1.1
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: | Mike Nguyen |  |  | Activity Log for First Design Project 1.1 (project research, development & documentation)
Full Student Number: | 301545780
Group Number: | G30
Members Relative Contribution: (estimate your contribution to this phase of the project) | 40%
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
| 5780 | 2026-02-15 | 0:00 | 1:00 |  | Reviewed DP1.1 guidelines PDF and confirmed required folder structure. Organized project directory with Documentation, SourceCode, Simulation folders. Verified naming conventions and removed spaces in paths. | 1
| 5780 | 2026-02-15 | 1:00 | 2:00 |  | Created Quartus project DP11 and imported VHDL design files (Adder_Baseline, CSA, FastRipple). Configured top-level entity and verified successful Analysis & Synthesis. | 1
| 5780 | 2026-02-15 | 2:00 | 3:00 |  | Generated SDC timing constraint file (adder.sdc) with create_clock constraint. Added SDC file into Quartus Timing Analyzer settings and recompiled project to ensure timing analysis works properly. | 1
| 5780 | 2026-02-15 | 3:00 | 4:00 |  | Ran Timing Analyzer reports for Cyclone IV device. Collected Setup Summary and Fmax Summary outputs and verified clock name detection. Checked slack values and confirmed timing constraint is applied. | 1
| 5780 | 2026-02-15 | 4:00 | 5:00 |  | Generated Resource Usage Summary reports for Baseline design. Exported timing/resource outputs to text files. Created transcript text files documenting tool output for baseline design compilation. | 1
| 5780 | 2026-02-15 | 5:00 | 6:00 |  | Repeated compilation and timing analysis process for CSA adder design. Exported Cyclone IV Fmax Summary, Setup Summary, and Resources reports into OutputFiles folder using required naming convention. | 1
| 5780 | 2026-02-15 | 6:00 | 7:00 |  | Repeated compilation and timing analysis for Fast Ripple adder design. Exported timing and resource reports. Verified outputs saved correctly and consistent with guideline format. | 1
| 5780 | 2026-02-15 | 7:00 | 8:00 |  | Reviewed Quartus output folders and corrected folder placement (Documentation/OutputFiles). Cleaned redundant auto-generated Quartus folders. Verified submission-ready directory structure. | 1
| 5780 | 2026-02-15 | 8:00 | 9:00 |  | Checked device requirement in DP1 document and confirmed need to evaluate Arria II device as well. Planned naming convention for Arria output files and prepared to rerun compilation for Arria II target. | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
9

## DP1.2
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: |  |  |  | Activity Log for First Design Project 1.2 (project revision)
Full Student Number:
Group Number: | Gxx
Members Relative Contribution: (estimate your contribution to this phase of the project) | %
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## DP2.0
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: |  |  |  | Activity Log for Second Design Project 2.0 (organisation & template reports)
Full Student Number:
Group Number: | Gxx
Members Relative Contribution: (estimate your contribution to this phase of the project) | %
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## DP2.1
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: |  |  |  | Activity Log for Second Design Project 2.1 (project research, development & documentation)
Full Student Number:
Group Number: | Gxx
Members Relative Contribution: (estimate your contribution to this phase of the project) | %
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## FP
Micro-Activities: 1) List of activites that are typically half-an-hour to two hours in duration; include relevant facts & details. 2) Ensure that you make a log entry at least every two hours. 3) If a task takes many hours, break up the activies into multiple log entries. Each log entry should describe your accomplishments for time blocks of approximately two hours.
Student Name: |  |  |  | Activity Log for Final Project (project research, development & documentation)
Full Student Number:
Group Number: | Gxx
Members Relative Contribution: (estimate your contribution to this phase of the project) | %
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of Micro-Activity ( include relevant facts and details) | Duration
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0